## Sheet1
Sprint 1 28.8.-1.9. | Role | what I did? | What am I doing? | Blockers
Matias | Electronic desing | research for electronic design | research for electronic design | understanding tho scope of the project | Porgramming
Ngoc | Electronic desing | set up Azure devops | research for electronic design | understanding tho scope of the project | Electronic desing
Konsta | Documentation | set up excel sheet and github etc. | research for electronic design | understanding tho scope of the project | Documentation
Sprint 2 4.9.-8.9 | Role | what I did? | What am I doing? | Blockers
Matias | Electronic desing | We as a team researsched the charasteristics of mosfets | researching | understanding the charasteristics of mosfet
Ngoc | Electronic desing | we as a team researched the charasteristics of mosfets | researching | understanding the charasteristics of mosfet
Konsta | Electronic desing | We as a team researsched the charasteristics of mosfets | researching | understanding the charasteristics of mosfet
This sprint contained a class where we went trought the basic charasteristics of mosfets.
Sprint 3 11.9.-15.9. | Role | what I did? | What am I doing? | Blockers
Matias | Porgramming | Wrote a program to read the cell voltages with stm32 | debuggin the program | -
Ngoc | Electronic desing | Testing mosfet charasteristic with LED's on a breadboard | designing the mosfet circuit | Understanding how to drive the mosfet
Konsta | Electronic desing | Designing of the op amp circuit, version 1 | designing the op amp circuit | Not fully understanding the point of the circuit
OWERVIEW: We did our first version of th op amp circuit desing and tested it on the bread board, unfortunately we had made mistakes and so it did not work properly.
Sprint 4 18.9.-22.9. | Role | what I did? | What am I doing? | Blockers
Matias | Porgramming | Programming the program to read the values from the op amp circuit | Testing the program if we get right values from the cell voltages | -
Ngoc | Electronic desing | builduing the mosfet circuit on a bread board | Testing the circuit | -
Konsta | Electronic desing | Redesigning the Op amp circuit | Building a new version of the circuit on a breadboard | Not knowing how the prevous version did not work
Sprint 5 25.9.-29.9. | Role | what I did? | What am I doing? | Blockers
Matias | Porgramming | Programming a program for reading the cell voltages. | starting to test if we can read value from a temperature sensor | -
Ngoc | Electronic desing | The previous design did not work so redesigning | builduing the circuit on a bread board | -
Konsta | Electronic desing | builduing the op amp circuit on the breadboard. | Testing if it works | Understanding how to connect all the circuits together
Sprint 6 2.10.-6.10. | Role | what I did? | What am I doing? | Blockers
Matias | Porgramming | Tested if the program works for reading the cell voltages. | Testing the program | -
Ngoc | Electronic desing | Builded a mosfet circuit on the bread board. | Testing if the build works. | -
Konsta | Electronic desing | Testing if the prevoius version worked correclty. | Starting to build the schematic on a copperboard. | Hating the copper board, might be that I will draw it on KiCAD.
Sprint 7 9.10.-13.10. | Role | what I did? | What am I doing? | Blockers
Matias | Porgramming | Tested the program and seems it workes with reading the values of voltages over resistors connected in series | Thinking how to implement the multiplexer | -
Ngoc | Electronic desing | The build worked correctly. | Drawing a schematic on KiCAD so that we can order the pcb. | Not knowing the Size of the pcb
Konsta | Electronic desing | Builduing the circuit on a copper board. | Started to draw schematic on KCiAD | Not knowing how to use the program
OVERVIEW: We have tested the program and it seems to work for reading the cell voltages. First working version of the op amp circuit on a bread board, also same with mosfet circuit.
Sprint 8 16.10-20.10. | Role | what I did? | What am I doing? | Blockers
Matias | Electronic desing | Researching the charasteric of the multiplexer and how to implement it into the op amp circuit | Researching how to add multiplexer into the op amp circuit. | -
Ngoc | Documentation | Draw a schematic of the mosfet circuit and then made also a .pcb file of the circuit. | Ordering the circuit from OSH park. | Waiting for the Pcb.
Konsta | Documentation | Learning how to use KiCAD. | Drawing the schematic on KiCAD | Not knowing how to turn the schematic into a pcb file.
Sprint 9 23.10.-27.10. | Role | what I did? | What am I doing? | Blockers
Matias | Electronic desing | Research of how to implement the multiplexer into the | Adding the multiplexer into the op amp bread board circuit. | -
Ngoc | Porgramming | Ordered the pcb from OSH Park. | programming a program for driving the mosfets.
Konsta | Electronic desing | Drew a schmeatic on Kicad. | Quitted usinng KiCAd and started to build new version of the op amp circuit on coppper board.
Sprint 10 30.10.-3.11. | Role | what I did? | What am I doing? | Blockers
Matias | Porgramming | Builduing the op amp circuit on the bread board, added the multiplexer. | programming how to read correct outputs from the multiplexer. | -
Ngoc | Electronic desing | Programming how to drive the mosfet circuit. | Testing the program. Also we recieved our pcb from OSH Park. | Debugging
Konsta | Electronic desing | SICK | SICK | SICK
OVERVIEW: We recieved the pcb from OSH Park, and we are now testing how to read the cell voltages through the multiplexer.
Sprint 11 6.11.-10.11. | Role | what I did? | What am I doing? | Blockers
Matias | Electronic desing | Programmed a program for reading the cell voltages from the op amp circuit but with the added multiplexer, and tested it. | Starting to build a new version of the op amp circuit on a copper board, because the version thath Konsta built did not work. | -
Ngoc | Porgramming | Tested the program and it did not work properly. | Still Working on the program. | Debugging
Konsta | Electronic desing | I was sick so not much that I did but the copper board build did not work, I made mistakes with the connection of the multiplexer. | Helping with the copper board builduing with Matias. | -
Sprint 12 13.11.- 17.11. | Role | what I did? | What am I doing? | Blockers
Matias | Porgramming | Did a new version on the copperboard. | Designing a circuit to add the temperature sensor so we can chack the cell temperatures. | -
Ngoc | Electronic desing | Worked on the program to drive the mosfets. | Looking into the shunt resistor to read the current coming out from the battery. | -
Konsta | Electronic desing | Helped Matias with the copper board design. | Starting to look into the visualization o the data recieved from stm. | Not knowing how to get the data to Graphana.
Sprint 13 20.11.- 24.11. | Role | what I did? | What am I doing? | Blockers
Matias | Porgramming | Adding the LM35 temperature sensor to the copper board. | programming how to read the tempreature from the battery. | Debugging, the temperature sensor seems to get weird values.
Ngoc | Electronic desing | Working on the shunt resistor circuit. | building the shunt resistor circuit. | -
Konsta | Electronic desing | Research of the graphana and visualization of the data. | Learning how to solder SMD's. | -
OVERVIEW: We now have fully functional mosfet pcb, we tested it with four LED's and it seem to work correctly. Op amp circuit is working correctly, we are able to read correct values from the cells(4 resistors connected in series.)
Sprint 14 27.11.-1.12. | Role | what I did? | What am I doing? | Blockers
Matias | Porgramming | Worked on the progam to read the temperature. | trying to implement modbus to sed the data from the stm. from a temperature sensor | Seems that there is a short somewhere on the board.
Ngoc | Porgramming | Added the shunt resistor circuit on a breadboard and tested it. | debuggin the program which drives the mosfets. | -
Konsta | Porgramming | Soledered the mosfets into the pcb. And begined to work with python script to get the data from stm. | Wiriting a python script to send the data from the stm into a database. I Downloaded PostgreSQL, so we can store the data, so that we cn visualize it on grpahana. | Not able the get the data to the database.
Sprint 15 4.12.-8.12. | Role | what I did? | What am I doing? | Blockers
Matias | Porgramming | research for electronic designWokred on the board and it seems there is still problems with the board, was th trying to scope the issues. | There is a prolem with reading the sensor, so we ripped it out and added it again. | -
Ngoc | Electronic desing | Testing the program which drives he mosfets. | Was able to fix the issues with the program and it is now working correctly. | -
Konsta | Electronic desing | Working on the visualization, having problems with getting th data to the db. | Debugging the script where to find the error which is causing this. | Not able to get the data to the db.
Sprint 16 11.12.-15.12. | Role | what I did? | What am I doing? | Blockers
TEAM | Porgramming | The team was working on their on scope of the project. | We are trying to put everything together so we can have a comlpete project. | Copper board is not working correctly. Not able o visualize the data on the graphana.
OVERVIEW: Unfortunately we ran out of time and did not complete the whole project. What we were able to do was to build the mosfet circuit and do a program which can drive mosfets as required. We were also able to build the op amp circuit so that we can read the cell voltages. We ran out of time and because of tht we were not able to fix the issues with the temperature sensor.